## Slide 1
2026 ICS Data Analytics & Automation Roadmap
Raghvendra Pratap Singh

## Slide 2
2026 ICS Audit-Related DA Use Cases

## Slide 3
Centralized Authentication Services (CAS)
AUDIT: 2026-GT-1111
FEB 16 – MAY 27, 2026
10 MAN-DAYS
Application Compliance for Authentication
Determine coverage of authentication services across applications
Identify non-compliant or missing integrations
Multi-Factor Authentication (MFA) Compliance
Assess MFA deployment across onboarded applications
Verify mandatory MFA enforcement
Desktop MFA (DMFA)
Review Windows Hello for Business (WHB) deployment
Assess 2FA compliance on company laptops/desktops
Verify Windows Hello for Business enrollment rates
Data Sources
CMDB, Entra (SSO), ForgeRock (MFA), WHB, Active Directory
Key Metrics
Application onboarding rates, MFA coverage, DMFA compliance

## Slide 4
Privileged Access Management (PAM)
AUDIT: 2026-GT-2222
APR 20 – JUL 24, 2026
15 MAN-DAYS
Key Focus Areas
Data Sources
OneVault, SuccessFactors, OneCert
Key Metrics
Session duration
Withdrawal frequency
SoD compliance
Rotation cycles
PID Session Management Identify anomalous sessions (>12 hours duration) Flag excessive PID withdrawals (>5 per day) Detect access during approved block leave periods | 2. Domain Approval & Release Controls Verify segregation of duties (approver ≠ requestor) Validate approval workflows
3. PID Access Assignment Review access grouping appropriateness Ensure principle of least privilege | 4. Password Rotation Compliance Validate rotation frequency adherence Confirm post-use password changes

## Slide 5
Ransomware & Malware Protection
AUDIT: 2026-GT-3333
JUN 1 – AUG 21, 2026
10 MAN-DAYS
Desktops, Laptops & Server Protection
Verify all company desktops protected by approved anti-malware solution
Verify all servers protected by approved anti-malware solution
Assess MAC devices and alternate endpoint protection
Coverage Analysis by Technology
SentinelOne (S1) deployment for servers
Microsoft Defender for Endpoint (MDE) deployment for desktops/laptops
Intune for mobile device management
Tanium for asset inventory cross-check
Protection Gaps
Identify unprotected or non-compliant endpoints
Detect devices with lapsed/outdated protection
Data Sources
SentinelOne (S1), MDE, Intune,
CMDB, Tanium
Key Metrics
Endpoint coverage %
Compliance %
Protection gaps
Device inventory accuracy

## Slide 6
2026 Automation Use Cases

## Slide 7
2026 Automation Use Cases - Ananya
Automation Use Case | Problem Statement | Proposed Solution | Benefit | Process | Effort | Impact | Data Repository | Dependency | Self‑Service/Analytics
UC‑01: Agentic AI Audit Workpaper Assistant | Auditors spend significant time manually drafting RCMs, control workpapers, RFIs, and report sections. Walkthrough discussions from meetings must be manually captured, transcribed, and structured, leading to inefficiencies, inconsistency, and risk of missed observations. | An agentic AI solution that consumes walkthrough transcripts and audit data to automatically draft RCMs, populate control workpapers, generate report sections, and create RFIs. Human‑in‑the‑loop review ensures accuracy, governance, and auditability. | 40–60% reduction in documentation effort, improved consistency of audit language, faster RFI cycles, better capture of walkthrough evidence. | Planning, Fieldwork, Reporting | High | High | Teams meeting transcripts, prior audit workpapers, RCM templates, control descriptions, audit timelines, Jira tickets | Human‑in‑the‑loop review model; access to transcripts and prior artefacts; template standardisation; governance and auditability requirements. | Analytics

## Slide 8
2026 Automation Use Cases - Ananya
Automation Use Case | Problem Statement | Proposed Solution | Benefit | Process | Effort | Impact | Data Repository | Dependency | Self‑Service/Analytics
UC‑02: Audit Scheduling Assistant | Audit scheduling and resourcing is currently manual and time‑consuming, requiring planners to reconcile auditor leave availability, skills/certifications, planned audits + team effort split, historical assignments (repeat domain fit), and auditor interests. | Build a scheduling assistant that ingests required dependencies, normalizes auditor roles (SAM/AM/Co‑Source) and then produces recommended staffing per audit. | Faster and more consistent scheduling, better skill‑to‑audit alignment, reduced conflicts with planned leave, improved continuity for repeated audits, and improved fairness/transparency by explicitly balancing interests and prior domain exposure. | Resourcing | Medium | High | leave_tracker.xlsx; skills.xlsx; planned_audits.xlsx; planned_assignments.xlsx; interests.xlsx | leave_tracker.xlsx, skills.xlsx, planned_audits.xlsx, planned_assignments.xlsx, interests.xlsx | Self‑Service Dashboard

## Slide 9
2026 Finalized Use Cases

## Slide 10
2026 ICS Domain DA Use Cases - Finalized
Use Case Name | Problem Statement | Data Repository | Self-Service / Analytics | Use Case Owner
Vulnerability Dashboard | Vulnerability data extraction for audits is manual and stakeholder‑dependent, leading to delays and inconsistent access across audit teams. | Service Bench | Self-Service Dashboard | Indraneel
Use Case Name | Vulnerability Dashboard | 
 | Due Date | Status
Stakeholder Engagement | 29th May 2026 | WIP
Received Raw Data | 12th June 2026 | Yet to receive
Reach out to DA Team | 17th June | Not Started
PoC | 26th June 2026 | Not Started
Implementation / Go-live | 31st July 2026 | Not Started

## Slide 11
2026 ICS Domain DA Use Cases - Finalized
All SAMs will have a performance goal to create DA use cases for their domain.
Use Case Name | Problem Statement | Data Repository | Self-Service / Analytics | Use Case Owner
IAM Dashboard | Application onboarded for central authentication is tracked manually | CMDB Entra, AD, MFA list, SSO list, One Cert info (onboarded, toxic, session management), One Vault dashboard (List of PIDs, last password change, users who can release etc. check with Neal he has the info) | Self-Service Dashboard | Vijay
Use Case Name | IAM Dashboard | 
 | Due Date | Status
Stakeholder Engagement | 11th June 2026 | WIP
Received Raw Data | 24th June 2026 | Yet to receive
Reach out to DA Team | 30th June 2026 | Not Started
PoC | 26th June 2026 | Not Started
Implementation / Go-live | 31st July 2026 | Not Started

## Slide 12
2026 ICS Domain DA Use Cases - Finalized
All SAMs will have a performance goal to create DA use cases for their domain.
Use Case Name | Problem Statement | Data Repository | Self-Service / Analytics | Use Case Owner
Agentic AI Audit Workpaper Assistant | Auditors spend significant time manually drafting RCMs, control workpapers, RFIs, and report sections. Walkthrough discussions from meetings must be manually captured, transcribed. | Teams meeting transcripts, prior audit workpapers, RCM templates, control descriptions, audit timelines, Jira tickets | Self-Service Dashboard | Ananya
Use Case Name | IAM Dashboard | 
 | Due Date | Status
Stakeholder Engagement | 8th May 2026 | Completed
Received Raw Data | 24th June 2026 | 
Reach out to DA Team | 30th June 2026 | Not Started
PoC | 26th June 2026 | Not Started
Implementation / Go-live | 31st July 2026 | Not Started

## Slide 13
2026 ICS Domain DA Use Cases - Finalized
All SAMs will have a performance goal to create DA use cases for their domain.
Use Case Name | Problem Statement | Data Repository | Self-Service / Analytics | Use Case Owner
UC‑02: Audit Scheduling Assistant | Audit scheduling and resourcing is currently manual and time‑consuming, requiring planners to reconcile auditor leave availability, skills/certifications, planned audits + team effort split, historical assignments (repeat domain fit), and auditor interests. | leave_tracker.xlsx; skills.xlsx; planned_audits.xlsx; planned_assignments.xlsx; interests.xlsx | Self-Service Dashboard | Ananya
Use Case Name | IAM Dashboard | 
 | Due Date | Status
Stakeholder Engagement | 11th June 2026 | WIP
Received Raw Data | 24th June 2026 | Yet to receive
Reach out to DA Team | 30th June 2026 | Not Started
PoC | 26th June 2026 | Not Started
Implementation / Go-live | 31st July 2026 | Not Started